## Production
Legend | Status | Code | Color | Count
| Completed | C |  | 0
| In Progress | WIP |  | 0
| Skipped | SK |  | 0 |  | Camso CPS Update
| Failed | F |  | 0
| To be Processed | TBP |  | 0
| Title | T |  | 0 |  | Actual Finish = Planned start+Actual Duration
|  |  | Total | 0 |  | Planned Finish=Planned Start+Planned Duration
Serial No. | Steps | Status | Planned Duration (in mins) | Actual Duration | Owner | Planned Start Time (GMT) | Planned Start Time (IST) | Planned Finish Time (GMT) | Actual Start Time (IST) | Actual Finish Time (IST) | Instructions | Reference History | PTC Case | Bug | Comments
1 | Pre Start activities (Source system - 11.0 With Oracle)
1.1 | Stop Windchill |  | 0:10 |  | ITC | 2020-05-30 04:30 |  | 2020-05-30 04:40 | 2020-05-23 10:00 | 2020-05-23 10:10
1.2 | Snapshot of server, backup LDAP |  | 1:00 |  | Camso | 2020-05-30 04:40 | 2020-05-30 04:40 | 2020-05-30 05:40 | 2020-05-23 10:10 | 2020-05-23 11:10
1.3 | Database Backup |  | 1:00 |  | Camso | 2020-05-30 04:30 | 2020-05-30 04:30 | 2020-05-30 05:30 | 2020-05-23 10:10 | 2020-05-23 11:10
2 | CPS Installation on QA (USCHAS56)
2.1 | Install by running PSI cps 16 and issue fixing |  | 3:00 |  | ITC | 2020-05-30 05:40 | 2020-05-30 05:40 | 2020-05-30 08:40 | 2020-05-23 10:10 | 2020-05-23 13:10
2.2 | Start Windchill 11.0 |  | 0:15 |  | ITC | 2020-05-30 08:40 |  | 2020-05-30 08:55 | 2020-05-23 13:10 | 2020-05-23 13:25
3 | Post Installation Activity
3.2 | ITC,Camso Smoke Testing |  | 1:00 |  | Camso | 2020-05-30 08:55 |  | 2020-05-30 09:55 | 2020-05-23 13:25 | 2020-05-23 14:25
3.3 | Checkpoint conference call |  | 0:15 |  | ITC , Camso | 2020-05-30 09:55 |  | 2020-05-30 10:10 | 2020-05-23 14:25 | 2020-05-23 14:40
3.4 | Go-Live Decision meeting - Final |  | 0:15 |  | ITC , Camso | 2020-05-30 10:10 |  | 2020-05-30 10:25 | 2020-05-23 14:40 | 2020-05-23 14:55
3.5 | Go-Live communication |  | 0:15 |  | Camso | 2020-05-30 10:25 |  | 2020-05-30 10:40 | 2020-05-23 14:55 | 2020-05-23 15:10
4 | Roll back | [8 empty] | 4
4.1 | Stop Windchill - App, LDAP |  | 0:10 |  | ITC | 2020-05-30 10:40 |  | 2020-05-30 10:50 | 2020-05-23 15:10 | 2020-05-23 15:20
4.2 | Restore File system (from *Restore Point 1.2 &1.3) |  | 4:00 |  | ITC | 2020-05-30 10:50 |  | 2020-05-30 14:50 | 2020-05-23 15:20 | 2020-05-23 19:20
4.3 | Start Windchill 11.0 - WindchillDS, Oracle DB,APP |  | 0:10 |  | ITC | 2020-05-30 14:50 |  | 2020-05-30 15:00 | 2020-05-23 19:20 | 2020-05-23 19:30
4.4 | ITC,ABB Smoke Testing |  | 0:10 |  | ITC , Camso | 2020-05-30 15:00 |  | 2020-05-30 15:10 | 2020-05-23 19:30 | 2020-05-23 19:40
4.5 | NO-Go-Live meeting |  | 0:15 |  | ITC , Camso | 2020-05-30 15:10 |  | 2020-05-30 15:25 | 2020-05-23 19:40 | 2020-05-23 19:55
Formulas:
Planned Finish Time (GMT) = [Camso CPS Update]+[Color]
Actual Finish Time (IST) = [Actual Start Time (IST)]:J28+[Color]:D28
Planned Start Time (IST) = [Camso CPS Update]+AK10
Actual Start Time (IST) = [Actual Finish Time (IST), row above]
Camso CPS Update = [Planned Finish Time (GMT), row above]

## Contacts
Contact Information
Camso Team Members | Email | Phone (Primary) | Available Time (EST) | ITC Infotech Team | Email | Phone (Primary) | Available Time (EST)
Steve | Steve.Martel@camso.co |  |  | Chetansingh Parmar | Chetansingh.Parmar@ITCINFOTECH.COM | 91-982 282 2206
Martin | Martin.St-Laurent@camso.co |  |  | Camso | Camso.Plmsupport@itcinfotech.com
Madhusanka | Madhusanka.Ranasinghe@camso.co |  |  | Rajvina Yakub | Rajvina.Yakub@itcinfotech.com
PTC Contacts / TS
IBM | Email | Phone (Primary) | Available Time (EST)